## Sheet1
Teaching and Learning Project Timeline |  | 2018 - 2019
|  | August |  |  |  | Sept. |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | # Days per content/ grade
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Stages of Curriculum Development | [45 empty] | TOTAL
Exploration/ Building Background | Action Book Study - Content Based Foreign Language Teaching | [44 empty] | 5 days | bar: January 2 to January 3; February 2 to February 4
| Action Book Study - Reading, Thinking, Writing about History | [44 empty] | 5 days | bar: October 4 to November 1; November 3; December 2 to December 3
Installation/ Curriculum Development | K-12 Counseling Task Force - Curriculum Recommendation | [44 empty] | 3 days | bar: October 2; November 2; January 3
| 6-8 Math PLC: Curriculum Development | [44 empty] | 3 days | bar: October 3 to October 4; February 2; April 1 to April 2
| 9-12 Math PLC: Curriculum Development | [44 empty] | 3 days | bar: October 2 to October 4; February 2 to February 3; April 1 to April 2
| K-12 Math Task Force - Curriculum Recommendation | [44 empty] | 5 days | bar: November 2; December 2; January 4 to February 1; April 1
| K-5 Report Card Task Force: TBD, per IT | [44 empty] | 5 days
Initiation | K-5 ELA PLC: Daily 5, IRLA, ReadyGEN | [44 empty] | 5 days | bar: August 4; October 1; February 1 to February 2; May 1
| 6-8 ELA PLC: Engage NY | [44 empty] | 5 days | bar: August 4; November 4; December 2; January 3; February 2 to February 4; March 2; April 4; May 2
| 9-12 ELA PLC invitational implementation: Engage NY | [44 empty] | 5 days | bar: August 4; October 4 to November 2; December 1; January 3 to January 4; February 2; March 2 to March 3; April 1; April 3 to April 4
| K-12 Library and ELA PLC: Collaboration | [44 empty] | 2 days | bar: August 4; February 2
| 9-12 CTE PLC: Coordination of Perkins grant mandates | [44 empty] | 6 days | bar: Sept. 1; October 4; December 1; January 1; February 4; May 1
Elaboration/ Implementation | K-5 Science Cadre: NGSS | [44 empty] | 3 days | bar: November 2; February 3; April 4
| 6-8 Science PLC: Units of Study | [44 empty] | 5 days | bar: October 4; January 2; April 1 to April 2; May 2
| 9-12 Science PLC: Chemistry/ Physics Units of Study | [44 empty] | 5 days | bar: October 1; December 1; January 4; February 2; April 2
| K-5 Health Enhancement PLC: Units of Study | [44 empty] | 8 days | bar: Sept. 4 to October 1; November 4; January 2; January 4; March 2; April 1; May 4
| 6-8 Health Enhancement PLC: Units of Study | [44 empty] | 3 days | bar: Sept. 3; October 4; December 2; January 2; March 2; April 2
Assessment | [45 empty] | TOTAL
Balanced Assessment System | Year 2 - STAR 360 Implementation | October 1: PD; November 3: HHS; February 2: PD; March 1: HHS; June 1: PD | 3 days, and testing windows
| Year 3 - SBAC Implementation with fidelity | [44 empty] | testing windows | bar: April 2 to May 4
Presentation at MT State Data Use Conference | bar: Sept. 3
| K-5 Report Card Task Force: TBD, per IT | [44 empty] | 5 days
NIC | [45 empty] | TOTAL
New Teacher Induction | Mentor Training | [44 empty] | 2 days | bar: August 3 to August 4
| New Teacher Orientation/ Induction(s) | [44 empty] | 9 days | bar: August 4; Sept. 3; October 1; October 3; January 2 to January 3; February 4; March 2; April 2