## Sheet1
Teaching and Learning Project Timeline |  | 2017 - 2018
|  | August |  |  |  | Sept. |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Stages of Curriculum Development | [45 empty] | TOTAL
Exploration/ Building Background | Action Book Study - Mathematical Mindset; Engage in Math | [44 empty] | 14 days | bar: Sept. 1 to Sept. 2; October 2; October 4 to November 2; November 4; March 2 to March 3; April 1 to April 2; April 4 to May 1; May 3
| Action Book Study - CTE Pathways; Bridging Soft Skills | [44 empty] | 5 days | bar: October 2; October 4 to November 1; November 3 to November 4
| Acton Book Study - Using Data in a Counseling Program | [44 empty] | 3 days | bar: October 4; November 2; November 4
| 6-12 Math Task Force - Prioritization of Standards | [44 empty] | 5 days | bar: January 4 to February 2; March 1; March 3
Installation/ Curriculum Development | K-12 Counseling Task Foce - National Standards Review | [44 empty] | 5 days | bar: October 1; November 2; November 4; March 2; April 3
| K-12 Counseling Curriculum Development | [44 empty] | 1 day | bar: Sept. 4
| K-12 Library Task Force - National Standards Review | [44 empty] | 5 days | bar: October 1; November 2; November 4; March 2; April 3
Initiation | K-12 ELA Task Force - Curriculum Resource Review | [44 empty] | 6 days | bar: August 4; Sept. 3; November 1; January 3; February 2; May 2
| K-12 ELA Curriculum Development | [44 empty] | 8 days | bar: Sept. 2; October 1; November 2; January 4; February 4; March 3; May 2 to May 3
| K-12 CTE Task Force - Audit Review and Implementation | [44 empty] | 6 days | bar: Sept. 1; October 4; December 1; January 1; February 4; May 1
Elaboration/ Implementation | K-12 Science with NGSS | [44 empty] | 8 days | bar: October 1 to October 2; November 2; January 2 to January 3; February 1 to February 2; April 2
| K-12 Health Enhancement | [44 empty] | 8 days | bar: October 4; December 1; January 3; February 1; March 1 to March 3; May 3
Other Priorities | [45 empty] | TOTAL
Balanced Assessment System | Year 1 - STAR 360 Implementation | bar: August 3; Sept. 1 to Sept. 4; January 2 to January 4; April 4 to May 4
Year 2 - SBAC Implementation with fidelity | bar: February 1; March 1; April 2 to May 4
Presentation at MT State Data Use Conference | bar: Sept. 4